## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
All major project milestones (data collection, model building, training) were completed successfully | Initial TensorBoard setup did not log scalar metrics properly (empty event file). | Automate TensorBoard setup with timestamped folders | Create a standard training script template that includes callbacks and TensorBoard logging setup automatically | Example
Achieved high model accuracy (~88%) for sign language recognition. | Some confusion in running TensorBoard logs and setting paths correctly. | Possibly collect more gesture data to push accuracy higher (above 90%). | Consider saving model at checkpoints every 500 epochs during very long training.
Model training was stable with no major crashes. | A few minor typos (e.g., to_categoric) caused early interruptions. | Build a checklist before training starts (logs attached, callbacks set). | Add a pre-training checklist (check logs folder, TensorBoard callback, validation splits).
Visualizations (loss/accuracy curves) were successfully generated and understood. | Lack of EarlyStopping or ModelCheckpoint could have caused resource wastage if crashes happened. | Always add EarlyStopping and ModelCheckpoint by default in future training. | Plan optional buffer time for setting up logs, retraining if logs fail.